## Outline draft 1
Date Due | Task | Time breakdown/schedule | Total Time Needed | Intermediate Steps | Resources/materials
2022-03-24 | Step D: Preregistration | Set up materials with dataset and variables in question ~3hrs at least one week prior | Possibly 10 hours or more depending on process | Identify which variables to use from data, what the specific research question is, and what statistics used to analyze it. | Downloaded leadership data
|  | Get familiar with the preregistration process and things needed for this. |  | Fill out preregistration form, including identifying hypotheses, variables, analysis plan, etc. | How various clusters of countries relate to the prevalent leadership styles. Do certain distributions of leadership arise in certain countries over others and how might it be related to cultural or geographical distinctions?
Complete process.
2022-04-07 | Step E: Data Cleaning + Analyses | : 7 hours, clean data and get the dataset ready for analyses | 15 hours | Look at prior research and investigate what type of analysis may be run.
: 8 hours, analyze data + make graphs
Recheck code and make sure that it is relevant to ?'s asked.
|  | This step requires most of the work, therefore plan to finish before 4/7 for extra time. |  | Get descriptive statistics + make chart (Culture, leadership, styles, other data relevant to ?'s )
Run code and recheck for errors.
Make graphs for the results
2022-04-14 | Step F: Write-up | Write the write up and make the graph | 3 hours | Check APA format and make sure things match that
|  | Check formatting and make sure it fulfills the various ?'s asked. |  | Describe results in paragraph format
Touch up graphs and add colors/details etc.
2022-04-19 | Step G: Make work public! | Upload to Github/OSF | 1 hour | Make readme file? otherwise, seems like just uploading code/analyses etc.
2022-04-26 | Step H: Present to class! | Create poster slide | 3 hours | Make poster slide to present to class
|  | Rehearse the presentation |  | Practice the presentation/make script/outline thing
Make sure things are explained clearly